## status as of october 2015
Status as of October 2015
City of Dreams Construction Programme Timeline as of October 2015
Construction Milestone | Status / Expected Completion Time
Design | Complete
Statutory Submissions and Approvals | Complete
Sub-contract Award and Procurement | Complete
Enabling Works and Foundation | Complete
Perimeter Wall | Complete
Corewall | March 2016
Exoskeleton Steel | September 2016
Other Superstructure/ Facades | December 2016
Building MEP, ABWF, Fit Out Works1 | March 2018
Statutory Inspections | April 2018

## update as of october 2016
Update as of October 2016
City of Dreams Construction Programme Timeline as of October 2016
Construction Milestone | Status / Expected Completion Time
Design | Complete
Statutory Submissions and Approvals | Complete
Sub-contract Award and Procurement | Complete
Enabling Works and Foundation | Complete
Perimeter Wall | Complete
Corewall | Complete
Exoskeleton Steel | October 2016
Other Superstructure/ Facades | March 2017
Building MEP, ABWF, Fit Out Works | February 2018
Statutory Inspections | March 2018

## status as of october 2015-1
Status as of October 2015
Original Studio City Construction Programme Timeline as of October 2015
Construction Milestone | Status / Expected Completion Time
Design | May 2016
Statutory Submissions and Approvals | November 2016
Sub-contract Award and Procurement | September 2016
Superstructure and Facades | June 2018
Building MEP, ABWF, Fit Out Works | June 2018
Statutory Inspections | July 2018

## update as of october 2016-1
Update as of October 2016
Studio City Construction Programme Timeline as of October 2016
Construction Milestone | Status / Expected Completion Time
Design | March 2017
Statutory Submissions & Approvals | December 2017
Sub-contract Award and Procurement | May 2018
Superstructure and Facades | October 2021
Building MEP, ABWF, Fit Out Works | October 2022
Statutory Inspections | January 2023

## update as of october 2016-2
Very truly yours,
Melco Crown Entertainment Limited
/s/ Geoffrey Davis
Geoffrey Davis Chief Financial Officer